# Meeting Minutes

Autumn Launch Project · Meeting 4

| Date | September 24, 2026, 2:00–3:30 pm | Place | Room 302 |
| --- | --- | --- | --- |
| Chair | Sam Taylor | Minutes | Morgan Reed |
| Attendees | Marketing: Sam Taylor, Alex Chen, Morgan Reed · Product: Jordan Lee · Supply chain: Casey Kim · Stores: Riley Park |  |  |

## 1. Topics and decisions

| Topic | Discussion | Decision |
| --- | --- | --- |
| Launch event plan | Cost and reach of the two options; stores prefer option B | Option B, budget capped at 450,000 |
| Materials delivery | The South batch is two days late, other regions on time | Supply chain to confirm reshipment by Sep 26 |
| Online content | October content awaits legal review, about three working days | First batch live by Sep 30 |

## 2. Action items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Confirm the South reshipment date | Casey Kim | 09-26 | In progress |
| Submit the detailed plan for option B | Alex Chen | 09-29 | Not started |
| Follow up legal review and schedule publishing | Morgan Reed | 09-30 | In progress |
| Roster the store support staff | Riley Park | 10-08 | Not started |

## 3. Other

The next meeting is on October 8 at 2:00 pm, same room. Owners please update their action items beforehand.