Project Plan

Website Redesign

| Owner | Marketing | Project manager | Alex Chen |
| --- | --- | --- | --- |
| Date | September 25, 2026 | Version | v1.0 |

# 1. Background

The current website dates from 2021. It is built around the company profile, buries the products and works poorly on phones; conversion has slipped to 1.2% over the past year. With the new brand identity in place, the site needs a redesign that makes it the main acquisition channel.

# 2. Goals

- Launch the new site for desktop and mobile by November 30.

- Raise conversion from 1.2% to 2.0% within three months of launch.

- Mobile pages load in under two seconds; usability score of 4.5 or better.

# 3. Scope

| In scope | Out of scope |
| --- | --- |
| · Information architecture and page design (about 24 pages) · Content migration and new copy · Front-end build and CMS integration · Analytics and the conversion funnel | · The in-product docs and help centre · Additional languages (phase two) · The online store and payments |

# 4. Schedule

| Phase | Work | Dates | Owner |
| --- | --- | --- | --- |
| Discovery | User interviews, competitor review, information architecture | 09-28 – 10-10 | Alex Chen |
| Design | Visual direction, page designs, design review | 10-11 – 10-31 | Jordan Lee |
| Build | Front end, CMS integration, content migration | 10-20 – 11-15 | Casey Kim |
| Test & launch | QA, performance tuning, staged rollout | 11-16 – 11-30 | Morgan Reed |

# 5. Budget

| Item | Amount | Notes |
| --- | --- | --- |
| Design contractor | 120,000 | Illustration and motion |
| Engineering | 150,000 | Three people for two months |
| Content and photography | 40,000 | Product photography and case studies |
| Testing and tools | 20,000 | Usability testing and monitoring |
| Total | 330,000 |  |

# 6. Risks

| Risk | Impact | Response |
| --- | --- | --- |
| More content to migrate than expected | High | Start the inventory two weeks early; move non-core pages in phase two |
| Repeated design reviews | Medium | Two review rounds per phase with a named decision maker |
| Unreliable third-party APIs | Medium | Fallbacks for the key integrations |

# 7. Acceptance

- Every page passes QA and renders correctly in the main browsers and on common phones.

- Mobile performance score of 90 or higher.

- Conversion events are complete and visible on the dashboard.