# Half-Year Work Report, 2026

Marketing · Prepared by Sam Taylor · July 10, 2026

# 1. Overview

In the first half the team worked along three lines: the brand refresh, new channels and membership growth. By June 30 we had delivered 54% of the annual targets; membership is ahead of plan, brand reach slightly behind.

# 2. Results

| Item | Annual target | Delivered | Progress |
| --- | --- | --- | --- |
| Brand reach (millions) | 12,000 | 5,600 | 47% |
| New members | 80,000 | 46,300 | 58% |
| Channel partners | 10 | 6 | 60% |
| Events | 24 | 13 | 54% |

- Brand refresh: the new visual system is live on the website, in stores and across the main channels; recall up 11 points in the survey.

- Channels: six regional partners signed, including the first in the South and Southwest.

- Membership: monthly sign-ups rose from 5,800 to 9,200 after the members’ day and the points programme launched.

# 3. Issues

- Brand reach fell short of plan: the Q2 media budget arrived late and online placements started five weeks behind.

- Some regional partners lacked training and materials, and their first-month sell-through was below expectations.

- Scheduling conflicts across departments stretched response times.

# 4. Plan for the second half

- Concentrate on the two key campaigns, the autumn launch and the year-end sale, to close the reach gap.

- Standardise the partner training kit and start monthly partner visits.

- Launch phase two of the membership programme, aiming at 90,000 new members for the year.

- Set up a fortnightly review with Product and IT to shorten response times.

# 5. Support needed

A further 300,000 in channel support for Q3, and two regional marketing specialists recruited with HR’s help.