## Slide 1
Internal proposal · Product
A closed loop for customer feedback
Alex Chen · September 25, 2026

## Slide 2
Where we are
02
6 weeks
The average wait from a frequent request to any response
Feedback is scattered across support tickets, sales chats and email, with no single entry point
No review cadence; whoever shouts loudest goes first
Customers cannot tell whether anyone is on it, so they ask again and again

## Slide 3
The proposal
Three parts, one loop
03
01
One inbox
Feedback from every channel lands on one board, deduplicated and tagged
02
Weekly review
Product, support and sales meet for 45 minutes and give every frequent request a status
03
Public roadmap
Customers see planned / in progress / shipped, and get told when it ships

## Slide 4
How we get there
04
1
Early October
Connect the three channels and set up the board
2
Mid-October
First weekly review; agree the status rules
3
November
Public roadmap live; notifications wired up
4
December
Review: response time and customer satisfaction

## Slide 5
Cost and return
05
Cost
Tools: board and notifications, about 20,000 a year
People: half a product manager, a third of a support agent
A 45-minute meeting every week
Return
Response time from six weeks to two
Duplicate feedback down 40%; fewer tickets
Renewal conversations backed by evidence; target renewals up 5 points

## Slide 6
Decisions needed
06
Approve a review group of one person each from product, support and sales, meeting weekly.
Approve the 20,000-a-year tool budget.
Authorise Product to publish the “planned” status externally.
If approved, we start on October 8 and report on the first phase at the end of December.